## Slide 1: Twenty Years Later ICPD Beyond 2014 A Briefing on the ICPD Beyond 2014 Review Process
13 February 2012

## Slide 2: Beyond 2014 Background
GA Resolution 65/234 extends the PoA beyond 2014 .
2014 CPD and UNGASS will assess the status of the PoA implementation.
Assessment will draw from a global review based on the highest quality data and analysis of the state of population and development.
UNFPA will lead the global review through a consultative process at national, regional, and global levels.
                Cont.

## Slide 3: Beyond 2014 Background
Three mandated reports will be delivered in September 2014:
1. Global report on review and way forward
2. SG’s report to the 2014 CPD
3. SG’s report to the Special Session (Index Report)
  There will be no renegotiation of the existing agreements.

## Slide 4: What are we aiming for?
Provide the most authoritative picture of the state of population and development in 2014 and beyond.
Outcome report serves as the major reference point for discussing, implementing and monitoring population and development policies and programmes beyond 2014.
CONT.

## Slide 5: What are we aiming for?
To renew political support for the PoA and the actions required for the full implementation of the ICPD goals;
A fully mainstreamed population and development agenda in the UN development agenda beyond 2015 (post 2015 MDGs framework);
An accessible agenda understood and owned by all partners and collaborators.

## Slide 6: Unique Opportunities
Methodology and expert engagement leads to cutting edge results and embracing of the outcomes as the basis for the UN development agenda beyond 2015.
An inclusive and fully participatory process leads to global and regional outreach (especially youth and civil society) and facilitates future implementation.

## Slide 7: A Post- 2015 UN Development Agenda
Establishment of senior task team by early 2012.
Terms of reference:
To assess progress by UN system, external stakeholders including the international financial institutions, civil society, academia and the private sector; and
To develop a system-wide vision and road map for the post-2015 agenda.
The analytical work and consultations would need to be concluded by the end of the 67th Session of the General Assembly in September 2013.

## Slide 8: Operational Review Process
Hold stakeholders meetings to agree on the overall approach.
Develop an indicators framework.
Develop and roll out the global survey instruments–core questionnaire, optional module and CIP.
National and regional validation of survey results (June 2012- August 2013).

## Slide 9: Tasks at Country Level
Work with Governments to manage the survey process at country level. This means:
Securing support for involving civil society and youth in national consultations/validation exercise.
Assisting Governments to collect data and complete questionnaires.
Strengthening the capacity of NGOs/youth.
                Cont.

## Slide 10: Tasks at Country Level
Ensuring inclusion of CSOs/youth in national delegations to review related meetings.
Guiding national messages to conferences.
Building innovative partnerships at country level for political and financial support.
Leveraging review into national dialogue on UN development agenda beyond 2015.

## Slide 11: Tasks at Regional Level
Work with Regional Commissions /Regional Partners to ensure alignment with agreed global process.
Identify region-specific issues for optional module.
Support Regional Commissions to source the country data, undertake the analysis, and draft the regional reports.
Support Regional Commissions to manage Regional Population Conference and its outcome.
Cont.

## Slide 12: Tasks at Regional Level
Support regional NGO consultations in early 2012 and back to back regional NGO population conference in 2013.
Ensure the inclusion of outcome of CSO regional meetings in 2013 in regional population conferences outcomes
Encourage other regional activities that support the quality of the review, including identifying key issues/themes and best practices for in-depth study/technical meetings

## Slide 13: Other Tasks
Taking advantage of 2013 Women Deliver conference for inputs – Kuala Lumpur (2013)
Dedicated global meeting on Youth in 2012 in Indonesia
Dedicated global meeting on Human Rights in 2013 in the Netherlands

## Slide 14: Communications
A communications plan is being rolled out by UNFPA.
A dedicated website: www.ICPDBeyond2014.com will serve as the main resource and a collaborative activity destination for all stakeholders.
Content on the internal site will ensure all staff are fully informed and updated.
Implementation of social media and networking will be utilized to reach the larger general public and specifically targeting youth.
Synergies will link ICPD website and other websites .
Notes:   The Communication Plan:
  Dedicated website for ICPD Beyond 2014 – serve as the main resource for stakeholders to access information related to events and documents and ensure visibility and increased support for ICPD Beyond 2014
  Internal site to ensure all staff are fully informed and information is stored and archived.
  Social media and networking
  Publications: 20th Anniversary Edition of the ICPD PoA, Publication on the GA outcomes/legislation (in addition to SWOP)

## Slide 15: Civil Society Partnerships
Letters sent to major CSO partners.
Involvement of Foundations and NGOs in consultation for the global review.
First global CSO consultation in Istanbul with youth representation.
                CONTINUED

## Slide 16: Civil Society Partnerships
January-June 2012: Undertake global mapping of NGOs and youth partners.
March-May 2012: CSO/Youth regional consultations for CSO planning and capacity strengthening.
June-September 2012: Capacity building for CSOs for participation in national validation workshops.

## Slide 17: Civil Society Partnerships
June-August 2013: CSO pre-regional population conference meetings; CSO participation as national delegates to population conferences
April/September 2014: CSO participation as national delegates to the 47th Session of 2014 CPD and the UN General Assembly Special Session.

## Slide 18
Thank you